## Gantt Data
WBS # | Task Name | Start Date | Days Needed | Assigned To | Status | Action Details | End Date
1.0 | Determine Team Roles | 2026-02-02 | 13 | Jacob, Seth, Harley, Conner | Complete | Define responsibilities | 2026-02-15
2.0 | Research and Planning | 2026-02-09 | 7 | Jacob, Seth, Harley, Conner | Complete | Component selection | 2026-02-16
3.0 | Mechanical Design (CAD) | 2026-02-16 | 28 | Jacob | Incomplete | Hopper & Dispenser on Bambu P2S | 2026-03-16
4.0 | Project Proposal | 2026-03-02 | 1 | Jacob, Seth, Harley, Conner | Complete | Draft and submission | 2026-03-03
5.0 | Wiring & Basic Motion | 2026-03-10 | 7 | Seth, Conner | Upcoming | Connect motor driver to MCU | 2026-03-17
M.1 | 33% Pres: Prototype Demo | 2026-03-17 | 1 | Team | Upcoming | Demonstrate motor turning dispenser | 2026-03-18
6.0 | RTC & Automation Logic | 2026-03-18 | 10 | Seth, Harley | Upcoming | Code 'Scheduled Feed' logic | 2026-03-28
7.0 | Enclosure & Level Sensing | 2026-03-28 | 10 | Jacob, Conner | Upcoming | Final housing and IR sensor | 2026-04-07
M.2 | 66% Pres: Automated Demo | 2026-04-07 | 1 | Team | Upcoming | Full autonomous cycle proof | 2026-04-08
8.0 | UI, Calibration & Polish | 2026-04-08 | 14 | Jacob, Seth | Upcoming | LCD menus and portion accuracy | 2026-04-22
9.0 | Final Testing & Docs | 2026-04-22 | 12 | Team | Upcoming | Stress test and manual prep | 2026-05-04
M.F | Final Presentation | 2026-05-06 | 1 | Team | Upcoming | Final Capstone Demo | 2026-05-07